## Instructions
Instructions Overview This document provides a template for an organization-wide annual work plan. The objective of this format is to fit an entire annual work plan and work tracking system within a simple and easily digestible format. This is useful for senior management, in terms of condensing more detailed work plans into a set of summary goals, key tasks, and annual targets, as well as for reporting using a 'dashboard' system to the board or key funders. Using this format requires, above all, that managers think critically about their major organizational priorities, key tasks and targets, and that they frame and present these in precise and clear language. The text presented on the next worksheet ('Sample Work Plan') provides an example of how an organization-wide work plan can be presented, while the third sheet presents a work plan template into which you can enter your own text to make this plan useful to your organization.
Column A: Goals This column provides the backbone for the organization's overall work plan - the major goals or 'pillars' of an organization's work and should be based on your strategic plan or business plan. The Goal should be a short statement, using as few words as possible. These goals lead into and frame the key tasks described in Column C.
Column C: Key Tasks This column identifies the key sets of initiatives or actions aimed at achieving the Goals laid out in Column A. These form the heart of the work plan, as these activities and their respective targets guide all actions as required to achieve the goals.
Column D: Status This column is the basic 'dashboard' status tool, which is changed and updated according to progress against the Key Tasks (Column C) and its respective Annual Targets (Column H). This can be updated monthly, or quarterly, as preferred by management. The column has both a color coding and letter explanation: Not started = activity not begun but on track as not yet scheduled to start (clear); In progress = activity begun and progressing fully according to schedule (blue); Slightly off track = progress slower than anticipated or delayed in relation to the schedule (yellow); Delayed = progress significantly impeded and requiring attention (red); Complete = Activity fully complete, target met (green).
Column E: Timeframe This column provides clear timeframes for each key task described in Column C. Timeframes can be set as either quarterly, if you do not yet know the exact timing, or monthly if you do.
Column F: Lead This column records the responsible person leading on each key task. Although multiple people may be involved in a key task, it is worth identifying one person who is accountable, acting as the point person and ensuring that deadlines are met.
Column G: Expected Outcomes This column provides the intended results from each key task or set of activities. It can be helpful to think through what change the key task will bring and clarify how that change allows you to achieve your overarching goal. For example, if a key task is to develop a communications strategy, it is useful to think through how the outcome will contribute towards achieving the goal of strengthening the organization. These outcomes can sometimes be found in existing project level documents such as grant proposals.
Column H: Annual Targets This column provides the monitoring metrics that can be used to measure progress against the key tasks, and ultimately against the organization’s strategic goals. Other project documents such as grant proposals or monitoring plans may already have some of these metrics clearly defined.
Column I: Resources This column highlights the funding available and the source of funding. It can be used to flag where there is a funding gap for some planned activities.
Column J: Notes Here the organization has space to comment on progress in terms of each key task, and to explain the status of the key task in relation to its annual target. It is particularly helpful to provide notes for key tasks where the status dashboard shows the tasks are off track or seriously delayed in order to explain the reasons for the delay and what steps will be taken to address it.

## Sample Work Plan
EAST AFRICA NATURAL RESOURCE ALLIANCE
2018 Annual Work Plan
Goals | S/N | Key Tasks | Status | Timeframe | Lead | Expected Outcomes | Annual Targets | Resources | Notes
1.0 Strengthen community land tenure in six target villages. | 1.1 | Facilitate participatory village land use planning, boundary demarcation, and development of village by-laws in six villages. | Delayed | Q2-Q3 | AT | Clarity on all village boundaries and legal basis for enforcement of community land use zones | * Digital LUPs in place in 6 villages * Approval of village by-laws by Village Assembly and submission to District Council | USAID ($10,000) | Timeline contingent on ability to resolve outstanding village boundary conflicts.
| 1.2 | Carry out six training workshops with Village Councils and Land Committees. | Slightly off track | March | AT | Established clear procedures for implementation and enforcement of village by-laws and land use rules, resulting in enforcement of grazing and other land use zones. |  | USAID ($10,000) | Ongoing boundary conflicts in villages D and F impacted by politics. Resolution not expected until after government elections in Dec 2018. Will be a priority for Q1-2 2019
2.0 Increase community revenue from tourism joint ventures | 2.1 | Facilitate joint venture agreements for construction of ecolodge in Enkiteng conservancy. | In progress | February | SR | Enkiteng conservancy JV agreement in place and base revenue paid | Enkiteng conservancy receives $15,000 in base revenue | Investor funded ($55,000) | Discussions around JV agreement progressing smoothly. Some friction with construction manager - support Enkiteng in building better relationship
| 2.2 | Faciliate the resolution of village boundary conflicts. | Complete | Q2 | PT | Boundary conflict resolved so conservancies can enter into contracts with investors. | A new grazing agreement between Osikiria and Orkejo conservancies. | Community paid ($4,000)
| 2.3 | Establish partnership with Conservation Business Advisors to provide customized training to field staff on joint venture negotiation and contract structure. | Not started | Q4 | SR | Improved staff capacity to facilitate community tourism joint ventures. | * Revenue agreement in place * Osikiria and Orkejo conservancies each receive at least $5000 in conservancy revenue |  | No budget currently allocated. Awaiting outcome of USAID grant, and will need to seek additional funding
3.0 Grow membership base of Community Based Organisations (CBOs) representing areas conserved by indigenous people and local communities | 3.1 | Consolidate and document Community Based Organisation membership levels. | Slightly off track | July | PT | Clarity about members' advocacy responsibilities depending on their level of membership | Membership levels handbook | Oxfam ($3,500) | Levels depend on matrix assessing CBO's connectedness to government and other influential stakeholders, as well as severity of land rights infringements local community represented by CBO is facing
| 3.2 | Carry out campaign to recruit all Piniandan community lands rights CBOs. | Not started | Q4 | BN | Increased ability to advocate at a national level about community land rights and a coordinated voice for ICCA conservation of land and resources. | 80% of ICCA CBOS are members (target of 184 organisations) | Not funded yet | 65% of ICCA CBOs are already members (150/ 230 organisations)
4.0 Organizational Development - Improve financial sustainability and resourcing through effective fundraising. Strengthen internal communications capacity and develop clear communications strategy. | 4.1 | Implement business plan. | Not started | Q4 | AT | 10% of core costs being generating through service provision payments by land rights CBOs. | $20,000 secured through service provision payments (10% of core costs of $200,000) | TNC ($15,000) | ICCA CBOs have received free support for the previous three years. Information sharing visit regarding the importance of cost recovery planned to all districts during Q2, however resistance is still anticipated. Develop plan to address anticipated objections
| 4.2 | Develop Communications Strategy to identify communications goals, target audiences, messages and channels of communication. | In progress | Q3 | SR | Increased interest in membership and improved ability to carry out advocacy at a national level. | Communications Strategy | TNC ($5,000) | New communications manager currently being recruited and expected to start in March 2016

## Template
ORGANIZATION NAME
20XX Annual Work Plan
Goals | S/N | Key Tasks | Status | Timeframe | Lead | Expected Outcomes | Annual Targets | Resources | Notes
Not started
Not started
Not started
Not started
Not started
Not started
Not started
Not started